## Work Permit
HEALTH and SAFETY WORK PERMIT | [5 empty] | JOB HAZARD ASSESSMENT (cont) |  |  | SITE LOCATIONS - FOR MULTIPLE SITES
PROJECT DETAILS | [5 empty] | Job Step | Hazards | Control Recommendation | Site ID | Anchor ID/PLA No. | Safety Officer | Project In-Charge | Name of Worker/Designation
Name of Sub Contractor | Ultegra Supplies and Services | Requesting Vendor | NOKIA SHANGHAI BELL |  |  | Testing and Troubleshooting | Eye Strain: Prolonged use of optical test equipment | Take regular breaks from the screen. Adjust lighting and monitor settings for optimal viewing.
Project In-Charge |  | Person In-charge
Project Safety Officer (attached COSH Certificate) | MELVIN ADOVE | Work Schedule |  | Work Time Period
Project Name | FIBERTIME | Start Date |  | Start Time |  | PAT/Acceptance Activities | fatigue | Ensure to schedule the PAT activities during daytime Avoid night activities
Work Location/s (fill site locations sheet for multiple sites) | Naic, Cavite | End Date |  | End Time
Tower Type | roofdeck | Brief Description of Work Service testing
ground base
WORK DETAILS
Is work to be done with high risk? |  | Work at Heights | scaffold | ladder | tower
| YES | NCII Cert of Scaffold Erector |  | WAH Rigger Certificate
| NO | Scaffold components available |  | Workers physically fit
Electrical Works
Heavy Lifting w/ Equipment /Excavation Works |  | NCII Cert of Electrician or ID of REE/RME
NCII Cert of Operator | Cert of Lift Rigger | LOTO Device |  | Insulated Tools
3rd Party Certification of Heavy Eqpt |  | Hot Works
Confined Space Works |  | NCII Cert of Welder |  | Fire Extinguisher
Certificate of SCBA Operator | Ventilation Equipment | OxyFuel flash back arrester installed |  | Fire Blanket
O2 and Gas Detector | Safety Line
Is there any harmful substance or nuisance release by the activty | YES | Fumes | Offensive Odors
| NO | Dust | Noise
|  | Sparks | Others:
Will there be Utility interruption (Water Electricity, HVAC, others) | YES | Specify affected utilities and affected areas
NO
N/A
Will there be waste generation: |  | Identify and list possible waste generated
YES
NO
List of tools and materials to be used
PPE | FIRST AID KIT
ODF
OPM
OTDR
Patchcord
List of workers
JAY PALASOL | ROSE EISELE BARBA
EDGAR PERALTA | MELVIN ADOVE
ROCKY MARZO TRIVIÑO
JANN ALEXIS AGULO
RODERICK REYES
MARK JOSEPH INOVERO
MARK JAYSON BRILLANTES
JOB HAZARD ASSESSMENT
Job Step | Hazard |  | Recommended Controls
Site Access | Slip, trip, and fall from uneven surface |  | Coordinate with lessor/ UDI security prior to entry. Ensure all permits are on hand. Only authorized person can enter the area
Prepare Work Area | Trips/Falls: Uneven surfaces, debris, inadequate lighting |  | Clear work area of debris, ensure adequate lighting, wear appropriate footwear (safety shoes)
Handling of Fiber Optic cables | Cuts/Lacerations: Sharp edges of fibers or connectors. |  | Wear cut-resistant gloves. Handle fibers with care
| Strain/Repetitive Motion Injuries: Repetitive hand movements (e.g., stripping, splicing). |  | Maintain proper ergonomics. Take breaks to avoid repetitive strain.
Use JHA Sheet for Additional Entries
REQUIRED PPE
Safety Shoes | Hardhat | Body Harness | Gloves
Welding Mask | N95 Masks | Goggles | Other PPE
ACKNOWLEDGEMENT
Prepared By: | Noted By |  | Approved By
| Ma. Lorena Angelica Tenorio |  | YES
Project Safety Officer | MNO/Project In-Charge |  | NO | MIDC Safety Officer
The Vendor/Contractor takes full ownership in ensuring the Health and Safety of its workers onsite by carefully assessing the activity. That the assigned Safety Officer and the Project In-Charge had identified the corresponding hazards and their appropriate safety controls. And all assigned personnel to this activity were made aware of their tasks, and the hazards and commits to carry out the safety controls. Any activity not included in the above scope will not be executed without a New Health and Safety Work Permit submitted
MELVIN ADOVE

## COSH Cert
Safety Officer Certificate's

## IDs
CONTRACTOR'S IDs